## 01-community-launch-checklist
Task | Category | Owner | Deadline | Status | Notes
What needs to happen | Which phase it belongs to | Who's responsible | When it's due | Not Started / In Progress / Done | Helpful context or links
Define community purpose and mission statement | Strategy | Community Manager | 2026-01-15 | Done | Keep it to 2-3 sentences. Answer: why does this community exist?
Choose primary platform (Discord / Circle / Skool) | Platform | Community Manager | 2026-01-18 | Done | Discord for real-time chat, Circle for courses, Skool for all-in-one
Set up Discord server and channel structure | Platform | Community Manager | 2026-01-20 | In Progress | Welcome, General, Resources, Events, Voice — start small
Create community guidelines and rules | Content | Community Manager | 2026-01-22 | Pending | Cover: behavior, spam, self-promo, dispute resolution
Design role hierarchy and permission system | Platform | Admin | 2026-01-25 | Pending | Free → Paid → VIP roles with escalating access
Set up moderation bots (MEE6, Carl-bot, or Dyno) | Platform | Admin | 2026-01-26 | Pending | Auto-mod, welcome messages, leveling, moderation logs
Write welcome message and onboarding sequence | Content | Community Manager | 2026-01-28 | Pending | DM on join + #welcome channel post + first-week sequence
Create content pillars and editorial calendar | Content | Content Creator | 2026-02-01 | Pending | Educational, community, promotional, cultural — 4 pillars minimum
Set up analytics tracking (member count, engagement) | Platform | Admin | 2026-02-01 | Pending | Statsbot or native Circle/Skool analytics
Plan launch week activities and events | Events | Community Manager | 2026-02-03 | Pending | AMA, icebreaker challenge, member spotlight, Q&A session
Build landing page and referral link infrastructure | Growth | Marketing | 2026-02-05 | Pending | Referral program setup with unique tracking links
Test full member experience end-to-end | QA | Community Manager | 2026-02-07 | Pending | Join as new user, go through onboarding, test all channels
Recruit 5-10 launch ambassadors | Growth | Community Manager | 2026-02-08 | Pending | Power users who'll invite others and seed conversations
Soft launch with invite-only cohort | Launch | Community Manager | 2026-02-10 | Pending | 15-20 members for 1 week to iron out issues
Hard launch public access | Launch | Community Manager | 2026-02-17 | Pending | Open doors full promo across email, social, website