## 07-event-planning-sop
Phase | Task | Owner | Timeline | Budget Item | Estimated Cost | Notes
Stage of the event lifecycle | What needs to be done | Who handles it | When it should be done by | What it costs money for | Expected spend | Details and dependencies
Planning | Define event goal and format | Community Manager | 6 weeks before | None | 0 | AMA, workshop, panel, or social hour? Align with community goal.
Planning | Choose date and time (consider timezones) | Community Manager | 6 weeks before | None | 0 | Poll members for best time. Avoid Monday mornings and Friday afternoons.
Planning | Set budget and resource needs | Admin | 5 weeks before | Event budget | 150 | Covers speaker honorarium, tool costs, and prizes if applicable.
Preparation | Confirm speakers or hosts | Community Manager | 4 weeks before | Speaker honorarium | 100 | Reach out 6 weeks out. Confirm 4 weeks out. Have a backup.
Preparation | Create event page and registration | Content Creator | 4 weeks before | Event platform (Luma / Zoom) | 30 | Set up registration, calendar links, and reminder emails.
Preparation | Design promotional graphics | Content Creator | 3 weeks before | Design tools | 20 | Canva templates or hire a designer. 3 social posts minimum.
Preparation | Write event script and talking points | Content Creator | 2 weeks before | None | 0 | Share with speakers 1 week before for feedback.
Preparation | Set up Discord event + voice channel | Admin | 1 week before | None | 0 | Schedule event in Discord. Create temporary voice channel if needed.
Preparation | Send calendar invites and reminders | Community Manager | 3 days before | Email tool (ConvertKit / Mailchimp) | 0 | Reminder sequence: 3 days, 1 day, 1 hour before.
Execution | Host event go-live | Community Manager | Day of | None | 0 | Arrive 15 min early. Test audio/video. Welcome attendees.
Execution | Live moderation and Q&A management | Admin | Day of | None | 0 | Screen questions, manage chat, handle technical issues.
Post-Event | Send thank-you and recording | Community Manager | 1 day after | None | 0 | Email + community post: recording, key takeaways, next steps.
Post-Event | Collect feedback survey | Community Manager | 2 days after | Survey tool (Google Forms / Typeform) | 0 | 3-5 questions. Offer incentive for completion (discount or resource).
Post-Event | Post recap and highlights | Content Creator | 3 days after | None | 0 | Write summary post in #announcements with clips and quotes.
Post-Event | Run retrospective with team | Community Manager | 1 week after | None | 0 | What went well? What to improve? Update SOP for next event.